## Ark1
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56
| Project | Info | level | Task | Start Date |  | End Date | Duration | 08.06.2020 | 09.06.2020 | 10.06.2020 | 11.06.2020 | 12.06.2020 | 13.06.2020 | 14.06.2020 | 15.06.2020 | 16.06.2020 | 17.06.2020 | 18.06.2020 | 19.06.2020 | 20.06.2020 | 21.06.2020 | 22.06.2020 | 23.06.2020 | 24.06.2020 | 25.06.2020 | 26.06.2020 | 27.06.2020 | 28.06.2020 | 29.06.2020 | 30.06.2020 | 01.07.2020 | 02.07.2020 | 03.07.2020 | 04.07.2020 | 05.07.2020 | 06.07.2020 | 07.07.2020 | 08.07.2020 | 09.07.2020 | 10.07.2020 | 11.07.2020 | 12.07.2020 | 13.07.2020 | 14.07.2020 | 15.07.2020 | 16.07.2020 | 17.07.2020 | 18.07.2020 | 19.07.2020 | 20.07.2020 | 21.07.2020 | 22.07.2020 | 23.07.2020 | 24.07.2020 | 25.07.2020 | 26.07.2020 | 27.07.2020 | 28.07.2020 | 29.07.2020 | 30.07.2020 | 31.07.2020 | 01.08.2020 | 02.08.2020
|  |  | Week 1 | Getting started
Project name |  | Semester project | 1.1. | Project Planning | 08.06 |  | 09.06 | 2 | bar: 1 to 2
Project leader |  | Yunus Talay | 1.2. | Pencil Sketches | 10.06 |  | 11.06 | 2 | bar: 3 to 4
Project Start Date |  | 2020-08-06 | 1.3. | Researching the web | 12.06 |  | 12.06 | 1 | bar: 5
Project End Date |  | 2020-02-08 | 1.4. | Finding the right fonts and colors | 13.06 |  | 13.06 | 1 | bar: 6
Project Length |  | 56 days | 1.5. | Make a decision about the final design plan | 14.06 | 21.06 | 14.06 | 1 | bar: 7
|  |  | Week 2 | Finishing the project plan
|  |  | 2.1. | Creating a project overview | 15.06 |  | 16.06 | 2 | bar: 8 to 9
|  |  | 2.2. | Work on the Gantt Chart | 17.06 |  | 19.06 | 3 | bar: 10 to 12
|  |  | 2.3. | Illustrating the project plan in Gantt Chart | 20.06 |  | 21.06 | 2 | bar: 13 to 14
|  |  | Week 3 | Creating the HTML
|  |  | 3.1. | Structuring the HTML file | 22.06 |  | 28.06 | 7 | bar: 15 to 21
|  |  | 3.2. | Creating a webpage with HTML | 22.06 | 08.06 | 28.06 | 7 | bar: 15 to 21
|  |  | 3.3. | Adding pages within the webpage | 22.06 |  | 23.06 | 2 | bar: 15 to 16
|  |  | 3.4. | Creating a webpage navigation | 24.06 |  | 24.06 | 1 | bar: 17
|  |  | 3.5. | Adding information to the page | 25.06 |  | 25.06 | 1 | bar: 18
|  |  | 3.6. | Adding page footer | 26.06 |  | 26.06 | 1 | bar: 19
|  |  | 3.7. | Finding and adding images | 27.06 |  | 28.06 | 2 | bar: 20 to 21
|  |  | Week 4 | Creating the CSS
|  |  | 4.1. | Working on WCAG principles | 29.06 |  | 29.06 | 1 | bar: 22
|  |  | 4.2. | Working on colors and typography | 30.06 |  | 01.07 | 1 | bar: 23 to 24
|  |  | 4.3. | Adjusting Images | 02.07 |  | 03.07 | 2 | bar: 25 to 26
|  |  | 4.4 | Styling the navigation | 04.07 |  | 04.07 | 1 | bar: 27
|  |  | 4.5 | Working on CSS index page | 05.07 |  | 06.07 | 2 | bar: 28 to 29
Week 5
|  |  | 5.1 | working on CSS tours page | 07.07 |  | 08.07 | 2 | bar: 30 to 31
|  |  | 5.2 | working on CSS trails page | 09.07 |  | 10.07 | 2 | bar: 32 to 33
|  |  | 5.3 | working on CSS about page | 11.07 |  | 12.07 | 2 | bar: 34 to 35
|  |  | 5.4 | working on CSS FAQ page | 13.07 |  | 13.07 | 1 | bar: 36
Week 6
|  |  | 6.1 | Finishing basic CSS | 14.07 |  | 14.07 | 1 | bar: 37
|  |  | 6.2 | responsive design - adjusting to different widths | 15.07 |  | 21.07 | 7 | bar: 38 to 44
|  |  | 6.4 | Working 320 - 768 px | 16.07 |  | 18.07 | 3 | bar: 39 to 41
|  |  | 6.5 | Working on 812 - 1399 px | 19.07 |  | 21.07 | 3 | bar: 42 to 44
Week 7
|  |  | 7.1 | Testing media queries | 22.07 |  | 23.07 | 2 | bar: 45 to 46
|  |  | 7.2 | Adjust everything perfectly | 24.07 |  | 25.07 | 2 | bar: 47 to 48
|  |  | 7.3 | Testing media queries | 26.07 |  | 26.07 | 1 | bar: 49
|  |  | 7.4 | Finishing all pages | 27.07 |  | 27.07 | 1 | bar: 50
|  |  | 7.5 | Testing media queries | 28.07 |  | 28.07 | 1 | bar: 51
Week 8
|  |  | 8.1 | Writing a report | 28.07 |  | 31.07 | 4 | bar: 51 to 54
|  |  | 8.2 | Finish and submit | 31.07 |  | 02.08 | 3 | bar: 54 to 56